Benton Irrigation District

River Pump Station Improvements

Construction Meeting Minutes

10/28/09

Attendees:  Brett Moore, Jim Bolten, Matt Steiner, Arin Atiyeh

Schedule Update

Some IS interior wall pieces to finish.  Retaining wall 4 footings completed with walls to be completed next Thursday.  Rock fall fencing and rock removal next week.  Excavation for the pump station wetwell in 2 weeks.

Submittals

Electrical re-submittal is coming form contractor soon.  Need RFI #6 response for MCC’s.  Arin to resend RFI.  Submittals needed on block building.

Old Business

- Arin noted that the Notice of change of conditions for rock removal in river has actual costs and has submitted for consideration.  Review of this request has not been completed.

- The change order for adding two elbows and restrained joint piping on the 20” pipe will be authorized.  Paperwork will be forthcoming.

- A change order for paving the driveway approach will be pursued, as this pavement is a requirement of the county.

New Business

1.	County will be contacted by Emery about OIE road closure possibilities for 36” pipeline.

Next Meeting

Wednesday, November 11 at 10 am.