Benton Irrigation District

River Pump Station Improvements

Construction Meeting Minutes

9/16/09

Attendees:  Brett Moore, Jim Bolten, Matt Steiner, Bill Martinak, Arin Atiyeh

Schedule Update

Form and place concrete for retaining walls 1 and 3.  Trash racks are on site and the slide gates are to be delivered next week.

Submittals

Pumps need a resubmittal with more information.  Electrical submittal review in process.  Also need landscape materials submittals.

Old Business

- The building permit still needs to be acquired and is in process.

- Arin noted that the Notice of change of conditions for rock removal in river has actual costs and has submitted for consideration.  Review of this request has not been completed.

- Pump payment schedule was discussed.  There is a concern over upfront payment.  A bond is to be requested for the upfront payment.

- Fish screens are ready to ship.  Appropriate storage was discussed.

- Power needs to be available for testing and start-up.  Concern was expressed over schedule affects lack of main power may have.  Matt noted that they should have an agreement shortly.

- Yakima Basin conservation tour is set for Sept. 24 at 1:45pm.  It would be acceptable if the tour parked at the trailer and walked down the easement to the east end of the project.

New Business

- The change order for adding two elbows and restrained joint piping on the 20” pipe will be authorized.  Paperwork will be forthcoming.

- A change order for paving the driveway approach will be pursued, as this pavement is a requirement of the county.

Next Meeting

Thursday, September 24 at 3pm.