Benton Irrigation District

River Pump Station Improvements

Construction Meeting Minutes

9/24/09

Attendees:  Brett Moore, Jim Bolten, Matt Steiner, Bill Martinak, Arin Atiyeh

Schedule Update

Form and place concrete for retaining walls 1 and 3.  Trash racks are installed and the slide gates are to be delivered friday.  Final concrete pour on walls 1 and 3 is scheduled for October 8 with coffer dam removal starting on October 12.

Submittals

Pumps need a resubmittal with more information.  Electrical submittal was returned.  Landscape seeding submittal to be provided later.

Old Business

- The building permit is in hand.

- Arin noted that the Notice of change of conditions for rock removal in river has actual costs and has submitted for consideration.  Review of this request has not been completed.

- Pump payment schedule was discussed.  There is a concern over upfront payment.  A bond is to be requested for the upfront payment.

- Fish screens are in BID yard.

- Power needs to be available for testing and start-up.  Concern was expressed over schedule affects lack of main power may have.  Matt noted that they should have an agreement shortly.

- Yakima Basin conservation tour is set for Sept. 24 at 1:45pm.  It would be acceptable if the tour parked at the trailer and walked down the easement to the east end of the project.

- The change order for adding two elbows and restrained joint piping on the 20” pipe will be authorized.  Paperwork will be forthcoming.

- A change order for paving the driveway approach will be pursued, as this pavement is a requirement of the county.

New Business

- 3 day concrete breaks were at 2,600 to 3,000 psi.  It was determined that placing the first 7 foot of backfill on both sides of the structure is acceptable at these strengths.

- Jim will check the potential for IS structure floating without backfill placed on the footing.

- The temporary power cable was stolen from the project site.  This cable was replaced and buried.

Next Meeting

Wednesday, September 30 at 10 am.