Benton Irrigation District

River Pump Station Improvements

Construction Meeting Minutes

9/9/09

Attendees:  Brett Moore, Jim Bolten, Matt Steiner, Bill Martinak

Schedule Update

Place concrete for last exterior IS walls and start interior IS walls.  Form and place concrete for retaining wall 1 footing.  Start excavation for retaining wall 3.  Misc. metals are on schedule for delivery.

Submittals

Pumps need a resubmittal with more information.  Electrical submittal review in process.  Need submittal on Ameridrain sheet drain and drain tile for foundation walls.  Also need landscape materials submittals.

Old Business

- The building permit still needs to be acquired and is in process.

- Arin noted that the Notice of change of conditions for rock removal in river has actual costs and has submitted for consideration.  Review of this request has not been completed.

- Pump payment schedule was discussed.  There is a concern over upfront payment.  A bond is to be requested for the upfront payment.

- Fish screens are ready to ship.  Appropriate storage was discussed.

- An in-water work window extension was discussed.  It was noted that we need to do all that we can to meet the current window, and revisit the issue at a later date, if needed.  We don’t know if they will grant an extension.

New Business

- Power needs to be available for testing and start-up.  Concern was expressed over schedule affects lack of main power may have.

- Yakima Basin conservation tour is set for Sept. 24 at 1:45pm.  It would be acceptable if the tour parked at the trailer and walked down the easement to the east end of the project.

Next Meeting

Wednesday, September 16 at 10am.